## Slide 1
Focus items : Change manual check in paper to auto check and record
Action | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar
1. Survey vendor data of each material |  |  |  |  |  |  |  |  |  |  |  | 
2. Grouping document |  |  |  |  |  |  |  |  |  |  |  | 
3. Set data base record item |  |  |  |  |  |  |  |  |  |  |  | 
4. Develop application from PDF to data base |  |  |  |  |  |  |  |  |  |  |  | 
5. Trial test |  |  |  |  |  |  |  |  |  |  |  | 
6. Set standard and training |  |  |  |  |  |  |  |  |  |  |  | 
7. Implement |  |  |  |  |  |  |  |  |  |  |  | 
Situation
Activity
KPI
Inspection data checking lead time Operator has to manual check inspection data every lot (~ 1300lot/ month)
SF06 : [QSD Incoming] Material Inspection data checking lead-time reduction
Check inspection data by manual
Manual input in data base
In-charge : Nichapatr, Kritsada Application : Opas P.
Survey vendor data of each material
Grouping document
Set data base record item
Develop application from PDF to data base
Trial test
Set standard
Training to operator
Report sys.
Trace sys.
Incoming DB
PDF  DB
DB utilization
PDF Analyze
Chart: Inspection data checking lead time (Hrs/month)
| Before | After
 | 166.5333 | 62.45
Reduce 62.5%
Item | Before | After
1. Vendor data checking by manual | 62.5 | 0.0
2. Stamp pass on vendor data | 20.8 | 0.0
3. Key inspection result data in data base | 20.8 | 0.0
4. Scan data | 10.4 | 10.4
5. Save vendor data in sharepoint | 10.4 | 10.4
6. Stamp pass on label box | 41.6 | 41.6
summary | 166.5 | 62.5
-104Hrs
Already finished and implemented
Closing

## Slide 2
QSD-Incoming : Improvement summary
Before
After
Application
Data base
Master format
Text Enable.pdf
Picture.pdf
O
X
Result OK/NG
Received Material
Scan QR code
PASS or NG
PDA
(60,000)
“NG”
Alert mail
Chart trend
Inspection summary
0.8Min/lot
1.8Min/lot
Material checking
History data
Receiving
Inspection data (PAPER)
Manual check
Application
Inspection data checking&record
Scan the evidence
Matching datasheet & Material box & Check Q’ty
8Min/lot
2.7Min/lot
Stamp to receive
Receiving slip & inspection result
Stamp to receive
10.7Min/Lot
4.5Min/Lot (2.6Min if implement all)
Wireless Scanner+PC notebook+cart
(5,900+30,000+5,000=49,000)
OR
5.3Min
Save in sharepoint
Key data
1.3Min
0.7Min
0.7Min
0.4Min
0.7Min
0.7Min
Material
Inspection
Data

## Slide 3
QSD-Incoming : Implementation
Temporally OCAP during trial period
Receive inspection data from Receiving
Upload file and run program
Result
(Can run program?)
Create new format
and run?
Yes
No
Yes
Shift | Name | Date | Remark
Shift A | Waree | 11/3/2020 | Can create new format. Can operate the application.
Shift A | Kwannapa | 11/3/2020 | 
Shift A | Dongjun | 11/3/2020 | 
Shift B | Supitcha | 11/3/2020 | 
Shift B | Thanyarat | 11/3/2020 | 
Shift C | Siyapha | 11/3/2020 | 
Shift C | Nittaya | 11/3/2020 | 
Start
Inspection result
“PASS”
End
Accept material
OK
Error
Inform Engineer to fix error or confirm data
Manual check data
No
Will optimize flow and revise WSD within Jun’20
(TWS-QSD013 Material Incoming Inspection)
2) Training to concern member
Already trained to all member 7psn.
They can operate by the new method
3) Implemented type list (in March’20)
Can’t apply all Lot&type due to take time to create master format (30min/type).
Already improve program (5min/type) and plan to finish create the master within Sep’20
First priority is 77%
Chart: 
| Interprosure | Package
Remaining | 30 | 11
Added master | 4 | 5
Total | 34 | 16
Completion of master format
Chart: 
| Interprosure | Package
By manual | 254 | 224
By application | 338 | 37
Total | 592 | 261
Implement on received lot Q’ty

## Slide 4
Chart: Material inspection data improvement trend
| Before | After (Plan) | After (Actual)
1. Vendor data checking by manual | 62.5 | 0 | 20.2685
2. Stamp pass on vendor data | 20.8 | 0 | 4.7486
3. Key inspection result data in data base | 20.8 | 0 | 4.7486
4. Scan data | 10.4 | 10.4 | 10.4
5. Save vendor data in sharepoint | 10.4 | 10.4 | 10.4
6. Stamp pass on label box | 41.6 | 41.6 | 41.6
summary | 166.5 | 62.5 | 92.1656
QSD-Incoming : Project summary
Item | Improvement | Before | After (Plan) | After (Actual) | Reduction (Actual) | Remark
1. Vendor data checking by manual | Check&Judge by application | 62.5 | 0 | 20.3 | -68% | -Main is IP from Kyocera 77% (720/933) -Remaining 2.7%(26/933) for creating master data format. -20% (187/933) is picture .pdf, cannot be improved by this project.
2. Stamp pass on vendor data | Record data into data base by application | 20.8 | 0 | 4.7 | -77% | 
3. Key inspection result into data base | Auto upload to data base | 20.8 | 0 | 4.7 | -77% | 
4. Scan data | N/A | 10.4 | 10.4 | 10.4 | 0% | 
5. Save vendor data in sharepoint | N/A | 10.4 | 10.4 | 10.4 | 0% | Need to keep in share point for evidence
6. Stamp pass on label box | Auto matching Box-to-data by application | 41.6 | 41.6 | 41.6 | 0% | Can’t be implemented yet! need to invest scanner & Notebook (reduce 54% total reduction 58%)
Summary |  | 166.5 | 62.5 | 92.2 | -45% | 
Unit : Hour/Month
Can reduce operation time
166.5Hr/M to 92.2Hr/M
or 45%
-62.5%
-45%

## Slide 5
SF06 : [QSD Incoming] Material Inspection data checking lead-time reduction
Project Summary
Output & Benefit
Method & Tools
Chart trend for each parameter
Can reduce operation time
166.5Hr/M to 92.2Hr/M
or 45%
Read PDF (Text) to Database : Adobe Acrobat SDK
Programing 1. Data Formatting : VBA
2. Auto Email : VBA
3. Update to DB : SQL
4. Web report : ASP.net & VB.net